## Development_Effort
Version History: Version: V1 Date created :12/ 2020 Version description: Draft version added with details of features available Version: V2 date updated 4/2021 Version description: Added sections on Reporting. Data integration,Recipes GA and SFMC Integration. Revised estimtes and description as per details available
Req Category | Category | Subcategory | Components | Number of Units | Design Effort | Build Effort per unit (in Hrs) | Total Build Effort (in Hrs) | Testing (in Hrs) | Deployment Effort | Total Efforts (in Hrs) | Assumptions
Orchestration | Customer 360 Audiences | Setup | Instance setup & User Creation | 1 | 9 | 16 | 16 | 4.8 | 0 | 29.8
| Customer 360 Audiences | Data Ingestion | Configure inbound Data Stream using SFMC connector | 1 | 6 | 24 | 24 | 7.2 | 1 | 38.2 | Assuming we will use SFMC adapter for engagement data and data extensions. Assuming Data from Email , Mobile connect & Mobile Push will be ingested
| Customer 360 Audiences | Data Ingestion | Configure File drop based data stream using S3 bucket of CS360 | 3 | 6 | 14 | 42 | 12.6 | 0 | 60.6 | Assuming File Drop Automation be taken care by other system. Assuming 3 file based data feeds to be configured | 331.7
| Customer 360 Audiences | Data Ingestion | configure CRM connector | 1 | 0 | 12 | 12 | 3.6 | 1 | 16.6 | contact , lead & account data
| Customer 360 Audiences | Data Mapping | Map raw DSOs (Data Source Object) to DMO (Data Model Object) | 11 | 0 | 6 | 66 | 26.4 | 0 | 92.4 | Map raw DSO created from SFMC + S3 based data Stream to respective DMO Assuming mapping has to be done to available 11 standard Data Model Object
| Customer 360 Audiences | Data Mapping | Attribute Mapping ( composite key) using Formula fields in DMO | 10 | 0 | 4 | 40 | 12 | 1 | 53 | 10 formula fields to be created in DMO
| Customer 360 Audiences | Data Mapping | Identity Resolution | 2 | 0 | 4 | 8 | 2.4 | 2 | 12.4 | Assuming set up match rules & reconciliation rules definitions to identify based on contact id & email.
| Customer 360 Audiences | Data Cleansing | Audience Filtering | 1 | 0 | 18 | 18 | 5.4 | 0 | 23.4 | Assuming Data cleansing to be done in CS360 on top of DSOs
| Customer 360 Audiences | Data Mapping | set up & map Custom Profile attributes in DMO | 3 | 0 | 9 | 27 | 8.1 | 0 | 35.1 | setup custom profile attribute in DMO from non-salesforce inbound data feed. Assuming 3 attributes
| Customer 360 Audiences | Segmentation | create segments based on mapped DMOs | 10 | 0 | 4 | 40 | 20 | 6 | 66
| Customer 360 Audiences | Insights | create calculated insights | 10 | 0 | 4 | 40 | 12 | 6 | 58 | Assuming we will create 10 calculated insights usings fields available in DMO tables.
Orchestration | Customer 360 Audiences | Activation Channel | Configure SFMC as an activation channel | 1 | 0 | 4 | 4 | 6 | 1 | 11 | Assuming segment activation on SFMC channel
| Customer 360 Audiences | Segment Activation | Segment Activation on Marketing Cloud using OOB CS360 to SFMC connector | 10 | 0 | 1 | 10 | 15 | 2 | 27 | Assuming segment activation on SFMC channel Assuming segments will be actiavted in batch Assuming segment activation is set to 12 hours
| Customer 360 Audiences | Channel Preference Management | Channel Preference Management | 1 | 6 | 24 | 24 | 3.6 | 2.4 | 36 | Considering the optin and preferences are captured in a DE via medium complex automations and cloud pages . Creation of data stream to sync these preferences to C360 Assuming the preferences is already setup considering it will be only one DE with all the customer preferences per BU considering email channel for communication
|  | TOTAL | [7 empty] | 559.5

## Assumptions
Sno | Assumptions
1 | No of Data Sources -
2 | data ingestion via Custom AWS vs OOB connector
3 | Setting up Role and permissions
4 | DSO to DMO data Mapping
5 | No of Formula Fields-
6 | Fields for Identity resolution
7 | No of reconciliation Rules
8 | No of segment with (Low / Medium / High) complexity
9 | No of calculated insights with Complexity of SQL
10 | Segment activation takes minimum of 12 hours
11 | Activation to be done via SFMC activation connector only
12 | Assuming Email , Mobile Connect and Mobile Push OOB bundle from SFMC connector in scope.
13 | Assuming No of custom Data Extension from SFMC BU to be onboarded.

## Question
Questions

## Questions (hidden)
S.No | Requirement Section | Question | Response
1 | Marketing Orchestration | Number of campaigns that we need to estimate for and how much reusablity?
2 | IP Warming | Would there ever be emails sent out to subscribers in bulk which would bypass the limits for daily sends? If yes we would need to go for IP Warming.
3 | Marketing Orchestration | How many types of campaigns do we need to build like Email Vs Direct mail VS SMS etc.?

## RampPlan (hidden)
Level | Office | Location | Role
|  |  |  | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16
|  |  |  | Discovery and Design | Build | [10 empty] | SIT |  | UAT & Go-Live | Hypercare
|  |  |  | SFMC Audience Builder Setup and Data Model Design | SPRINT 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4
Sr. Manager | Offshore | India | Delivery Manager | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Manager | Offshore | USI | Manager | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Sr. Consultant | Offshore | USI | Tech lead (SFMC US) | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | Application Developer 1 (SFMC) | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | Application Developer 2 (SFMC) | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | Application Developer 3 (SFMC) |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
BTA | Offshore | USI | Application Developer 4 (SFMC/Front End)* | Week5: 45; Week6: 45; Week7: 45; Week8: 45; Week9: 45; Week10: 45; Week11: 45; Week12: 45; Week13: 45
BTA | Offshore | USI | Application Developer 5(SFMC) | Week5: 45; Week6: 45; Week7: 45; Week8: 45; Week9: 45; Week10: 45; Week11: 45; Week12: 45
Sr. Consultant | Offshore | USI | SFMC Testing Resource 1 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | SFMC Testing Resource 2 |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
*SFMC Developer having Front End skills.