## Development_Effort
Version History: Version: V1 Date created :12/ 2020 Version description: Draft version added with details of features available Version: V2 date updated 4/2021 Version description: Added sections on Reporting. Data integration,Recipes GA and SFMC Integration. Revised estimtes and description as per details available
Req Category | Category | Subcategory | Components | Number of Units | Design Effort | Build Effort per unit (in Hrs) | Total Build Effort (in Hrs) | Testing (in Hrs) | Deployment Effort | Total Efforts (in Hrs) | Assumptions
Orchestration | Interaction Studio | Setup | Dataset Activation Configuration Set up Deploy IS pixel on the site create atrribute & dimensions create user attributes Validate Event Stream Segment Taxanomy Set up Sitemap Blueprint document | 1 | 54 | 9 | 9 | 2.7 | 0 | 65.7 | Assuming all marketing sites have same structure. 1 dataset for Dev/QA which will be used in lower environments. 1 dataset for production. Sitemap Blueprint will finalize page types, catalog, events, user & account attributes and content zones. Post sign-off on sitemap blueprint, any new requirements would require additional effort. Assuming Site structure is same.
| Interaction Studio | Sitemap | Configure Page types | 5 | 0 | 12 | 60 | 18 | 1 | 79 | Assuming 5 pagtypes based on finalized sitemap blueprint
| Interaction Studio | Sitemap | Set up Content Zone | 1 | 0 | 5 | 5 | 1.5 | 0 | 6.5 | 1 content zone on one page based on finalized sitemap blueprint |  | 155.7
| Interaction Studio | Sitemap | Profile attributes (UCP)/ Identity Mgmt | 1 | 0 | 9 | 9 | 2.7 | 0 | 11.7 | Assuming upto 5 profile attribute setup for identity merge. Assuming all identity attributes to be available at page level while sending events
| Interaction Studio | Sitemap | Set up Listener Events (de-anonymization) | 1 | 0 | 18 | 18 | 5.4 | 0 | 23.4 | 2 listener events for identity merge based on finalized sitemap blueprint
| Interaction Studio | Sitemap | Catalog Setup with Datalayer | 1 | 0 | 27 | 27 | 8.1 | 0 | 35.1 | Catalog setup for product & category itemtype with 10 dimensions & 5 attributes Assuming catalog setup to be done for voila.com Assuming catalog setup to be done using datalayer. Assuming catalog setup not required for marketing sites.
| Interaction Studio | ETL Feed Setup | Upload ETL feeds for user/Product/Transaction/Dimension/categories | 4 | 36 | 9 | 36 | 36 | 5.4 | 113.4 | SFTP user has to be setup. Assuming that upto 20 attributes to be brought in using the USER ETL feature. Data transformation to be done in source system. Dependent on ETL/Feed upload feature to build up Product Catalog. If not available, then 2 weeks of nurturing time would be required for product catalog to be build which would be set up by sitemap. Will be using Gears provided by Salesforce and any development or usage of custom gears are out of scope.
Orchestration | Interaction Studio | Audience Building | Create qualification & supression segments | 20 | 0 | 2 | 40 | 60 | 1 | 101 | Campaign's segment & suppression will be based on web data. Design effort is once per brand. Assuming 4 segments to be created per promotion. Assuming 5 experiences per promotion. Assuming 1 inclusion & 1 exclusion segment per experience.
| Interaction Studio | SFMC Integration | Segment Activation on Journey Builder | 20 | 0 | 1 | 20 | 4 | 1 | 25 | Assuming segment to be built and sent to SFMC using the add to Journey Builder on Join feature. Assuming effort in IS to setup and validate identities, segment build and activation. efforts not included to build out API event, Automation (query activity,etc) and journey build in SFMC. Additional effort might be needed to warm up dataset's server. Assuming segment is already built & identity attributes are set up. Assuming JourneyBuilder Gear is available and active.
| Interaction Studio | Data Integration | Use Segment export feature to export a segment into SFTP Location | 1 | 16 | 35 | 35 | 10.5 | 8 | 69.5 | Export Interaction Studio segment data to a CSV file on a daily basis. Upto 50 attributes can be included. SFTP account and user are steup
| Interaction Studio | Data Integration | Use SFTP import feature to import data into IS | 1 | 16 | 35 | 35 | 10.5 | 8 | 69.5 | Import data via a CSV file into Interaction Studio on a daily/hourly basis. Data transformation into IS's ingestible format has to be done at source system. Upto 50 attributes can be included. SFTP account and user to be steup.
| Interaction Studio | Data Integration | Use OOB connector to import a segment into IS | 1 | 8 | 24 | 24 | 7.2 | 8 | 47.2 | Import segment data via OOB connector, CS360A into Interaction Studio. Assuming Marketing cloud data to be brought in via CS360A connector in IS. Assuming segments are created at CS360A. Connector to be released in June 2021.
| Interaction Studo | Reporting | Enable OOB Reports to get insights into campaign performance | 1 | 8 | 5 | 5 | 1.5 | 1 | 15.5
Orchestration | Interaction Studio | Web Template Design- Global Template | HTML Template Cross-device compatible CSS Adding Campaign Analytics | 1 | 18 | 36 | 36 | 10.8 | 5.4 | 70.2 | Will create one template with for 1 website/brand. Assuming will create a pop-up template per use case. Assuming minimum modification in global template
Orchestration | Interaction Studio | Build Web Campaign | Build Web Campaign for configuring Texts, images, CTAs & experiences with audience control | 1 | 4 | 18 | 18 | 5.4 | 2.7 | 30.1 | Use the Pop-up template to configure 5 different experiences (5 each for brands with EN & FR) A/B test Campaign with 5 experiences to be setup. | mention campain type for Sobey's
| Interaction Studio | Mobile SDK setup | Configure Mobile SDK with Business App (Android / IOS) | 1 | 40 | 70 | 70 | 21 | 10.5 | 141.5 | set up 1 android / IOS app with IS SDK
| Interaction Studio | Tagging Support | Tagging Support in dataLayer & SDK config | [6 empty] | 90 | Assuming Deloitte will Support in dataLayer & SDK tagging & Tech specs per brand.
| Interaction Studio | Event API | Create custom event API for data ingestion | 6 | 9 | 16 | 96 | 4.8 | 14.4 | 124.2 | create 6 event API to send actions back to IS
|  | TOTAL | [7 empty] | 1118.5

## Dependencies
Sno | Dependencies
1 | Will need access prod instance of interaction studio so that dynamic datalayer values can be fetched.
2 | Deciding on org strategy. If using Marketing cloud with multiple BUs, advised to have dataset : BU :: 1:1. Considering that lower environment of website is used for dev and qa, the environment should be stable.
3 | IS javascript snippet to be deployed on every page of the website.
4 | Deciding on which attributes can be captured through datalayer versus DOM. As a best practice, data can be captured using - datalayer > meta tags > DOM
5 | Defining primary and secondary user attributes to set up Unified Customer Profile.
6 | Defining customer identification points (sign up points on site) for identity stitching
7 | Defining page types based on site structure.
8 | Setting up dimensions and attributes(planning the catalog structure) prior to doing the sitemap.
9 | Stable DOM as sitemap and events will be configured using html elements.
10 | Creatives and campaign design (attributes that can be configured and defined on template) to be defined by client. Approved creatives like Background Image, Header, body texts , CTA text , Logo etc.
11 | Segment qualification and suppression rules to be defined by client.

## Question
Questions
Are we looking at importing/exporting data via these connectors?(Google/ Linkedin/ Facebook/Pinterest) Assuming that identity management is not in scope for the connectors.
What will Locale refresh be leveraged for?
Will a FE resource be required or can it be assumed that once template is created, it will be handed over to client team to make final changes wrt responsiveness
Assuming that a fresh template will be created per use case. Is this accurate?
Does VOC email refer to welcome email/ email sent on signing up for the first time

## Questions (hidden)
S.No | Requirement Section | Question | Response
1 | Marketing Orchestration | Number of campaigns that we need to estimate for and how much reusablity?
2 | IP Warming | Would there ever be emails sent out to subscribers in bulk which would bypass the limits for daily sends? If yes we would need to go for IP Warming.
3 | Marketing Orchestration | How many types of campaigns do we need to build like Email Vs Direct mail VS SMS etc.?

## RampPlan (hidden)
Level | Office | Location | Role
|  |  |  | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16
|  |  |  | Discovery and Design | Build | [10 empty] | SIT |  | UAT & Go-Live | Hypercare
|  |  |  | SFMC Audience Builder Setup and Data Model Design | SPRINT 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4
Sr. Manager | Offshore | India | Delivery Manager | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Manager | Offshore | USI | Manager | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Sr. Consultant | Offshore | USI | Tech lead (SFMC US) | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | Application Developer 1 (SFMC) | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | Application Developer 2 (SFMC) | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | Application Developer 3 (SFMC) |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
BTA | Offshore | USI | Application Developer 4 (SFMC/Front End)* | Week5: 45; Week6: 45; Week7: 45; Week8: 45; Week9: 45; Week10: 45; Week11: 45; Week12: 45; Week13: 45
BTA | Offshore | USI | Application Developer 5(SFMC) | Week5: 45; Week6: 45; Week7: 45; Week8: 45; Week9: 45; Week10: 45; Week11: 45; Week12: 45
Sr. Consultant | Offshore | USI | SFMC Testing Resource 1 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Consultant | Offshore | USI | SFMC Testing Resource 2 |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
*SFMC Developer having Front End skills.